## M-1 Tasks
INFRASTRUCTURE TASKS | Area / Component | Status | Notes
Set up Digital Ocean Server | Server | Done
Configure SSH security | Server | Done
Set up DO box to run ASP vNext (ASP 5) | Server | Done |  | 1
Deploy Test app to verify ASP/MVC/EF work on Linux | Server | Done | Working, but fails on database. Next step is to install mysql and change the connection string | 2
Install MySQL / MariaDB | Database | Done | … but I removed it. Not supported by Entity Framework (yet) | 3
Redirect test app to MariaDB/MySQL & verify working | Database | ABORT |  | 5
APPLICATION TASKS | Area / Component | Status | Notes
Download/install required librarys for asp.net 5 | Tools | Done | Note: May need to do this again on Linux if the site won't run.
Create ASP .Net 5 (vNext) sample site. | App | Done
Connection String for MySQL/MariaDB and Verify Connection | App | FAIL | MySQL and Oracle aren't supported yet. Need to revise plans. | 4
Create new ASP MVC "empty" project | App | ABORT | Should be clean; Minimal default controllers/views/ (Ideally "empty") | 6
Commit base default app to repo | App | ABORT | w/ verified working connection string | 7
MISC TASKS | Area / Component | Status | Notes
Database table schemas | Docs | ABORT |  | 8
Database Creation SQL script | Database | ABORT | Dependency on schema | 9
Create site deployment pipeline | Pipeline | ABORT | Will likely need a way to get the app from windows -> Linux and publish. Will require removing the IIS references from project.json and Program.cs | 3

## M-0.5
INFRASTRUCTURE TASKS | Area / Component | Status | Notes
Set up Cloud Site on GearHost | Server | Done
Set up Database on GearHost | Database | Done
Verify app connection string to database | Database | Done
APPLICATION TASKS | Area / Component | Status | Notes
Creat default ASP .NET application | Application | Done
Test publishing of application to gearhost | Publish | Done
Review default models/controllers - remove the cruft | Application | In Progress
Commit base default app to repo | Repo
MISC TASKS | Area / Component | Status | Notes
Database table schemas | Docs | Done
Database Creation SQL script | Database |  | Not critical - using Entity Framework (Code-First)
Enable Database migrations | Database | Done

## M0 - Account Mgmt
ADMIN FEATURES | Area / Component | Status | Notes
Create Admin View (and model/controller if required) | Admin Controller | Done | Admin view created and restricted by role.
Change Admin password | Admin Controller | Done
Change User password | User Controller |  | Better solution: implement forgot password reset request.
Delete User account | User Controller | Done
Promote User to Admin or Organizer | Admin Controller | Done
Remove User From Role | Admin Controller | Done
Create Admin Game controller | Game Controller | Done
Modify Users list to display their roles (admin, TO, etc.) | User Controller | Done
Change Admin/Users so that it displays the user avatars | Users, Global | Done | Refactored this to use a custom Html Helper for images.
USER FEATURES | Area / Component | Status | Notes
Register | User Controller | Done
Login | User Controller | Done
Logout | User Controller | Done
Change Password | User Controller | Done
Change Avatar | User Controller | Done | Show avatar setting on the account management page.
View User Profile | User Controller | NEXT | Ties to item below.
View Users List | User Controller | NEXT | Should to filter by game (Warmachine by default). Also think about how to store/retrieve score summary data.
Create UserGames model/table | User Model | REVISIT | Requires some design. End goal is to support multiple games. Easier to do now rather than later. Should give it a better name than UserGames. E.g. GameLogs
Move firstname, lastname, faction to UserGame table/model | User Model | Done | User model has avatar field; UserGame doesn't need a faction; GameLog entries will derive a faction logo from the army for that game entry.
New UserGame controller for adding games/data. | UserGame Controller | In progress | Started, but needs further work. DELAYED. PART OF M1.
Show User name, avatar image on index after login | Home Controller | Done | New view created. Need to add buttons/links. (Subscribe to game, log game entry)
User Partial View for insertion on multiple pages |  | Done | Show Avatar, Name, e-mail …
MISC | Area / Component | Status | Notes
Allow OAUTH2 Logins from Facebook | Login/Auth |  | See StartupAuth.cs
Allow OAUTH2 Logins from Google | Login/Auth |  | See StartupAuth.cs
Modify/Update user model to include missing fields | User Model | Done | May need future updates to support faction avatar.
Add any missing/required fields from model to registration page | Registration View | Done
Add default avatars to database |  | Done | Logos live on webserver and are loaded based on a path string derived from a stored faction db entry.
Obscure/encrypt connection string ID/Password | Security |  | Connection string is in Web.Config --> Will show up on github. See this for solution: http://stackoverflow.com/questions/5630352/avoiding-asp-net-passwords-in-github
Fix code-first migrations on server |  | Done
Reminder: Move jquery scripts to a .js file and remove from register view | Registration View | Done
Implement "Forgot Password" | User password
Fill in content for legal page and hook up the link properly. | Legal view. | Done

## M1 - Game Data
ADMIN FEATURES | Area / Component | Status | Notes
USER FEATURES | Area / Component | Status | Notes
MISC | Area / Component | Status | Notes

## Links
ASP .NET CORE on LINUX
https://theobjectifiedprogrammer.com/install-vnext-on-digitalocean-ubuntu-droplet/
https://www.microsoft.com/net/core#windows
https://github.com/dotnet/core/blob/master/Documentation/prereqs.md#windows-dependencies
https://blog.tonysneed.com/2015/05/25/develop-and-deploy-asp-net-5-apps-on-linux/
https://docs.asp.net/en/latest/publishing/linuxproduction.html
http://stackoverflow.com/questions/38205662/unable-to-publish-binaries-in-net-core
https://support.rackspace.com/how-to/installing-mysql-server-on-centos/
https://www.linode.com/docs/databases/mariadb/how-to-install-mariadb-on-centos-7
https://www.digitalocean.com/community/tutorials/how-to-create-a-new-user-and-grant-permissions-in-mysql
https://docs.efproject.net/en/latest/providers/index.html
http://www.asp.net/mvc/overview/older-versions/using-oauth-providers-with-mvc

## Notes
Need to publish as "root". Not sure why, probably a permissions problem somewhere. But that's what works.
Systemd starts the app on start
Supervisord installed to run/monitor the application
Firewall??
EF for DotNet Core does not support MySQL (yet). Neither is Oracle. Fuck.